## Sheet1
Financial Analysis for Comun-ity
Created by: Elio Testa e Michele Iannucci |  |  | Date:25/10/2022
Discount rate | 7%
Assume the project is completed in Year 0 |  |  | Year
| 0 | 1 | 2 | 3 | Total
Costs | 2950 | 2300 | 2300 | 2300
Discount factor | 1 | 0.93 | 0.87 | 0.82
Discounted costs | 2950 | 2139 | 2001 | 1886 | 8976
Benefits | 2955 | 4072 | 4310 | 4748
Discount factor | 1 | 0.93 | 0.87 | 0.82
Discounted benefits | 2955 | 3786.96 | 3749.7 | 3893.36 | 14385.02
Discounted benefits - costs | 5 | 1647.96 | 1748.7 | 2007.36 | 5409.02 | NPV
Cumulative benefits - costs | 5 | 1652.96 | 3401.66 | 5409.02
ROI | 60.26%
Payback in Year 0
Assumptions
Costs | Number of | Cost/Hours | Hours | Total
Project Manager | 2 | 14 | 25 | 700
Team Member | 5 | 9 | 50 | 2250
Total of Costs (year 0) |  |  |  | 2950
Maintenance + Release | Number of | Cost/Hour | Hours | Total
Project Manager | 1 | 14 | 25 | 350
Team Member | 3 | 9 | 50 | 1350
Hosting |  |  |  | 600
Total Maintenace cost each year |  |  |  | 2300
Commissions | Year 0 | Year 1 | Year 2 | Year 3
Wallet transfer commision estimate | 20 | 20 | 20 | 20
Commission rate | 1.2% | 1.2% | 1.2% | 1.2%
Transaction estimate | 0 | 400 | 500 | 600
Total Commissions for each year | 0 | 1152 | 1440 | 1728
Reserves |  | Cost | Percentage
Contingency Reserve |  | 8976 | 10% | 897.6
Cost Baseline |  |  |  | 9873.6
Management Reserve |  | 8976 | 10% | 897.6
Total Budget |  |  |  | 10771.2
Subscriptions | Year 0 | Year 1 | Year 2 | Year 3
Subscription price | 10 | 10 | 10 | 10
Subscription estimate | 0 | 75 | 80 | 95
Total Subrsciptions for each year | 0 | 750 | 800 | 950
Benefits | Year 0 | Year 1 | Year 2 | Year 3
European Investment PNRR (90%) | 2655 | 2070 | 2070 | 2070
Commissions on payments | 0 | 1152 | 1440 | 1728
Subscription | 0 | 750 | 800 | 950
Private Investitors | 300 | 100 | 0 | 0
Total of Benefits for each year | 2955 | 4072 | 4310 | 4748