## Sheet3
Technical
Sponsorship
Communications
Schedule
Budget
Contracts
Scope
Accept
Transfer
Mitigate
Avoid
Share
Exploit
Enhance

## ACTION ITEMS
Notes on Accessibility: Tested and Best Accessible Through JAWS Version 11 or Higher. For definitions, please refer to the worksheet labeled DEFINITIONS.
FUNDING No: |  | FULL PROJECT NAME: | Comun-ity | PROJECT MANAGER: | Testa Elio Iannucci Michele |  | TECHNOLOGY DEPLOYED: | Mid-Tier (Application)
PRINT ON LEGAL SIZE PAPER
ACTION ITEM No. | DATE OPENED | DESCRIPTION | PRIORITY | RESPONSIBLE PARTY | DUE DATE | COMPLETION DATE | NOTES | STATUS
AI1 | 2022-11-03 | Accorpamento Requisiti Funzionali Login e Logout | H | Tutti i Membri del Team | 2022-11-04 | 2022-11-04 | / | Closed
AI2 | 2022-11-03 | Aggiunta RF Registrazione | H | Tutti i Membri del Team | 2022-11-04 | 2022-11-04 | / | Closed
AI3 | 2022-11-03 | Aggiunta RF Accertamento Professionista | H | Tutti i Membri del Team | 2022-11-04 | 2022-11-04 | / | Closed
AI4 | 2022-11-03 | Aggiunta RNF Invio E-Mail | H | Tutti i Membri del Team | 2022-11-04 | 2022-11-04 | / | Closed
AI5 | 2022-11-10 | Aggiunta RF Notifica all'Admin | H | Tutti i Membri del Team | 2022-11-11 | 2022-11-11 | / | Closed
AI6 | 2022-11-29 | Aggiunta RNF | H | Tutti i Membri del Team | 2022-12-02 | 2022-12-02 | / | Closed
AI7 | 2022-12-02 | Aggiunta Design Goal | H | Tutti i Membri del Team | 2022-12-05 | 2022-12-05 | / | Closed

## DEFINITIONS
FUNDING No.
The funding number is assigned by the OFM (Office of Financial Management) once the project is approved for funding.
Click or Activate This Cell (Press Enter) To Go To This Area.
PROJECT MANAGER
Individual responsible for creating, updating and maintaining the integrity of the action items list. Individual assigned with the responsibility of documenting action items and orchestrating updates to the action items list with those responsible and accountable for their assigned action items.
Click or Activate This Cell (Press Enter) To Go To This Area.
TECHNOLOGY DEPLOYED
Technology deployed is the category or component of a system under development in this project. The categories of technologies currently available are Mid-tier (application), Desktop, Mainframe, Database, Infrastructure, Office Automation or Telecommunications.
Click or Activate This Cell (Press Enter) To Go To This Area.
ACTION ITEM No.
A unique identifier in a numbering system assigned to an action item. The identifier should be used for reference or for cross-reference in the future to navigate through action items. Example: AI01, AI02, AI03...
Click or Activate This Cell (Press Enter) To Go To This Area.
DATE OPENED
The date that the action was deemed necessary through a collective approach. A collective approach is used when tasks - that need to be completed - are identified by project stakeholders, and there's a mutual agreement that these tasks will be carried out by the individual responsible for the action item.
Click or Activate This Cell (Press Enter) To Go To This Area.
DESCRIPTION
An action item is a cooperative agreement among project stakeholders that a certain action need to take place to carry out a project. An example of an action item description is "To correct errors identified on three web pages before proceeding into the implementation phase." In this case, the action item is necessary to be completed prior to entering the implementation phase as members have proposed in a meeting.
Click or Activate This Cell (Press Enter) To Go To This Area.
PRIORITY
The level of priority in this case addresses which action items are the most sensitive to the project, and need to be resolved with the highest level of attention and/or precedence. Depending on the project, action items are to be addressed with timeliness, highest degree of focus and/or tactfulness. "H" denotes High Priority. "M" denotes "Medium Priority." "L" denotes "Low Priority."
Click or Activate This Cell (Press Enter) To Go To This Area.
RESPONSIBLE PARTY
The individual responsible for ensuring that an action item is carried out in the agreed upon manner.
Click or Activate This Cell (Press Enter) To Go To This Area.
DUE DATE
The date the action item is expected to be closed.
Click or Activate This Cell (Press Enter) To Go To This Area.
COMPLETION DATE
The actual date the action item was closed.
Click or Activate This Cell (Press Enter) To Go To This Area.
NOTES
Progress of an action item to date. Start with the date, and then briefly describe what has been accomplished. EXAMPLE: "MM/DD/YYYY - Enter Notes."
Click or Activate This Cell (Press Enter) To Go To This Area.
STATUS
In this section, please select which action items have been Open (not resolved yet,) Cancelled (No Action Deemed Necessary,) Closed (resolved,) Deferred (put on hold.)
Click or Activate This Cell (Press Enter) To Go To This Area.